## Agile Plan
Sprint | User Story ID | User Story Description | Priority (MoSCoW) | Dependency | Status | Deliverable
Sprint 1 | US-01 | Design and develop transaction ingestion REST APIs | Must | None | Done | Transaction API
Sprint 1 | US-02 | Persist transactions with lifecycle states in Oracle DB | Must | US-01 | Done | Transaction Table
Sprint 1 | US-03 | Implement SUCCESS / FAILED / PENDING transaction lifecycle | Must | US-02 | Done | Lifecycle Logic
Sprint 2 | US-04 | Implement rule-based fraud detection engine | Must | US-03 | Done | Fraud Rules
Sprint 2 | US-05 | Add velocity and failed-attempt fraud rules | Must | US-04 | Done | Velocity Rule
Sprint 2 | US-06 | Expose APIs to fetch fraud, success and failed transactions | Must | US-04 | Done | Query APIs
Sprint 3 | US-07 | Generate synthetic transaction dataset for ML | Must | None | Done | CSV Dataset
Sprint 3 | US-08 | Train Random Forest fraud detection model | Must | US-07 | Done | ML Model
Sprint 3 | US-09 | Deploy ML model as Flask microservice | Must | US-08 | Done | ML API
Sprint 3 | US-10 | Integrate ML predictions with Spring Boot service | Must | US-09 | Done | Hybrid Fraud Engine
Sprint 4 | US-11 | Implement account blocking after multiple failed transactions | Must | US-06 | Done | Blocked Accounts Table
Sprint 4 | US-12 | Auto-unblock accounts after 24 hours | Must | US-11 | Done | Unblock Logic
Sprint 4 | US-13 | Add admin authentication (login/signup) | Should | US-01 | Done | Auth Module
Sprint 4 | US-14 | Send email alerts on fraud detection | Should | US-10 | Done | Email Alerts
Sprint 4 | US-15 | Build analytical dashboards for transactions | Should | US-06 | Done | Dashboard UI